## Project Planner
Sprint 2 - Speed
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity | Staff Members(s) | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Sign out robot | Nicholas | 1 | 5 | 1 | 5 | 100%
Develop a plan (Gant chart) | Kathryn | 1 | 5 | 2 | 2 | 100%
Build/write requirements table | Kathryn | 1 | 5 | 2 | 2 | 100%
Requirements confirmation | Kathryn | 1 | 5 | 3 | 1 | 100%
Algorithm | Kathryn | 1 | 5 | 2 | 1 | 100%
Flowchart | Joseph | 1 | 5 | 2 | 1 | 100%
Hardware | Joseph | 1 | 5 | 4 | 1 | 100%
Software | Joseph | 1 | 5 | 4 | 1 | 100%
Code | Nicholas | 1 | 5 | 2 | 3 | 100%
Test Plan | Nicholas | 1 | 5 | 2 | 1 | 100%
Actual testing | Nicholas | 1 | 5 | 2 | 3 | 100%
Staffing plan | Kathryn | 1 | 5 | 2 | 1 | 100%
Executive Summary | Kathryn | 1 | 5 | 4 | 1 | 100%
Product description | Kathryn | 1 | 5 | 3 | 1 | 100%
Presentation | Nicholas, Kathryn, Joseph | 1 | 5 | 1 | 5 | 10%